## Attachment Bc - Document (Part
OBJECTID | ENQUIRY NUMBER | WORKS | PRIORITY | DISTRICT | SUBURB | LOCATION TYPE | STREET_NUMBER | STREET_NAME | FRONTAGE | STREET_FRONTAGE | BLOCK | SECTION | UOS_NAME | HERITAGE | TREE REGISTERED | DESIGNATED | SPECIES | TREE_INT | COLLECTOR | COLLECTION_DATE | HEIGHT_m | DBH_cm | HEIGHT | HEIGHT_SC | HEALTH | HEALTH_SC | STRUCTURE | STRUCTURE_SC | USEFUL LIFE EXPECTANCY | ULE_SC | RISKZONE | RISK_SC | RISKSCORE | TCCSRISK | TRUNK_ROT | BRANCH_ROT | TREE_UNSTABLE | SPLIT_CRUTCH | BRANCH_FAILURE | ADV_DECLINE | UTILINEPRX | FOOTPATH | VERGE | ROAD | KERB | UTILINECON | STFURNIT | LINESIGHT | BEEHIVE | BIRDS_NEST | UTILBOX | UNDERGROUND | PRIVATE_TREE | PRIVATE_PLANTING | REMOVAL MARK | REM_KERB_MARK | REMOVAL REASON | REM_APPROVED | DATE_SIGNED | ASSGND_TO | PROGRAM | REMOVAL TYPE | JOB_LOT | COMPANY | REPLANT_REQUIRED | PLANTING_MRK | NO_REPLANT | REPLANT_SPECIES | STUMP_REMOVED | STUMP_REM_DATE | BARREL_REMOVED | BARREL_REM_DATE | WORKS_COMPLETED | WORKS_COMP_DATE | STATUS | TTM | CONTRACTOR_COMMENTS | TCCS_COMMENTS | COMMENTS | GlobalID | created_user | created_date | last_edited_user | last_edited_date | POINT_X | POINT_Y | CreationDate | Creator | EditDate | Editor | Poison required | Audit comment | x | y
3630 |  | Removal | Low | Central | Yarralumla | Open Space Tree | [9 empty] | Yes |  |  | Josh Drew | 4/3/2019, 9:45 AM | 20 | 45 | Very Large >20 (5) | 5 | Poor (3) | 3 | Failed (5) | 5 | Short >50 (0) | 0 | Major (4) | 4 |  |  | Yes |  |  |  | Yes | [17 empty] | Storm Damage | Yes | 4/3/2019, 9:47 AM | Inhouse |  | Standard | [12 empty] | Barrel and stump remaining |  |  |  |  | 4956eff8-9239-4f30-b426-5be509c35b5e | josh.drew_ACTGOV | 2019-04-03 | josh.drew_ACTGOV | 3/4/2019, 9:57 AM |  |  | 5/14/2019, 9:49 AM | ut_ACTGOV | 6/6/2019, 12:15 PM | ut_ACTGOV |  |  | 16596219.16 | -4204482.138
3631 |  | Removal | Medium | Central | Yarralumla | Open Space Tree | [9 empty] | Yes |  |  | Josh Drew | 4/3/2019, 9:50 AM | 30 | 60 | Very Large >20 (5) | 5 | Poor (3) | 3 | Failed (5) | 5 | Short >50 (0) | 0 | Moderate (3) | 3 | [24 empty] | Storm Damage | Yes | 4/3/2019, 9:51 AM | Inhouse |  | Standard | [12 empty] | Barrel and stump remaining |  |  |  |  | 94cffca1-52db-4037-89e9-0ecd9d7b2a92 | josh.drew_ACTGOV | 2019-04-03 | josh.drew_ACTGOV | 3/4/2019, 9:57 AM |  |  | 5/14/2019, 9:49 AM | ut_ACTGOV | 6/6/2019, 12:15 PM | ut_ACTGOV |  |  | 16596267.09 | -4204498.984
3632 |  | Removal | Medium | Central | Yarralumla | Open Space Tree | [9 empty] | Yes |  |  | Josh Drew | 4/3/2019, 9:55 AM | 30 | 150 | Very Large >20 (5) | 5 | Poor (3) | 3 | Failed (5) | 5 | Short >50 (0) | 0 | Moderate (3) | 3 | [24 empty] | Storm Damage | Yes | 4/3/2019, 9:56 AM | Inhouse |  | Standard | [12 empty] | Barrel and stump remaining |  |  |  |  | 9aec2f97-0e49-4cc5-b54b-5f3f7212999f | josh.drew_ACTGOV | 2019-04-03 | josh.drew_ACTGOV | 3/4/2019, 9:56 AM |  |  | 5/14/2019, 9:49 AM | ut_ACTGOV | 6/6/2019, 12:15 PM | ut_ACTGOV |  |  | 16596268.92 | -4204500.926
3634 |  | Removal | Medium | Central | Yarralumla | Open Space Tree | [9 empty] | Yes |  |  | Josh Drew | 4/3/2019, 10:00 AM | 30 | 70 | Very Large >20 (5) | 5 | Poor (3) | 3 | Failed (5) | 5 | Short >50 (0) | 0 | Moderate (3) | 3 | [24 empty] | Storm Damage | Yes | 4/3/2019, 10:02 AM | Inhouse |  | Standard | [12 empty] | Barrel and stump remaining |  |  |  |  | c2152937-bb8b-44f7-a0a5-42b0e314ee8a | josh.drew_ACTGOV | 2019-04-03 | josh.drew_ACTGOV | 3/4/2019, 10:02 AM |  |  | 5/14/2019, 9:49 AM | ut_ACTGOV | 6/6/2019, 12:15 PM | ut_ACTGOV |  |  | 16596312.11 | -4204521.522
7186 |  | Removal | Urgent | Central | Yarralumla | Open Space Tree |  | Weston Park | Back | [7 empty] | Pinus radiata |  | Josh Drew | 5/26/2020, 10:09 AM | 30 | 85 | Very Large >20 (5) | 5 | Dead (5) | 5 | Failed (5) | 5 | Short 0-10 (5) | 5 | Moderate (3) | 3 | 23 | Very High | [6 empty] | None | [15 empty] | Storm Damage |  |  | Inhouse |  |  |  |  | No |  | Over Crowding |  | Yes | 2020-05-26 | Yes | 2020-05-26 | Yes | 2020-05-26 | Job completed |  |  |  | Tree failed and was hung up in 2 other radiata. Entered by Olivia Anderson | b3094284-f8ac-4a7c-b2bd-6f6b62f26f09 | [6 empty] | 5/26/2020, 10:20 AM | oliviaandersonactgov | 6/4/2020, 1:59 PM | oliviaandersonactgov |  |  | 16595904.65 | -4204973.289
8347 |  | Removal | Medium | Central | Yarralumla | Open Space Tree |  | Behind Royal Canberra Golf course | [8 empty] | Pinus radiata |  | Brent Schwartzkoff | 11/20/2020, 3:43 PM | 22 | 150 | Very Large >20 (5) | 5 | Dead (5) | 5 | Fair to Poor (2) |  | Vacant (0) | [30 empty] | Contract | DTRP 2020 |  | Job Lot 15 |  | No | [9 empty] | To be removed |  |  |  |  | 9b2f104d-9b4f-4139-91b2-af18fe424e8e | [6 empty] | 11/20/2020, 3:47 PM | lisaflederisactgov | 1/6/2021, 1:09 PM | lisaflederisactgov |  |  | 16596109.13 | -4204514.746